## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Working on the coding for the Login page Have the main code finished, but still working on image | 
Status as of | 6-Mar-19
Business Lead | Jim Worth
Project Manager | Romeo Sturkey
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/6 | 2/13
Design |  | 100% | 2/13 | 2/27
Coding |  | 10% | 3/24 | 
SIT - System Test |  | 0% | 4/6 | 
UAT User Acceptance Test |  | 0% | 4/6 | 
Training and Doc |  | 0% | 4/13 | 
Deployment |  | 0% | 4/22 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Started first coding assessment
2 | Have most of the hard code completed
3 | Login header, username box, password box, login buttton
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Finish the login page with a background image
2 | Work on coding the next page
3 | Continue and finish coding all of the pages
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Background image will not come up | Med | Low | Research a way to solve it. | name | Med | 3/24
2 | Coding Errors with other pages | High | Med | Trial and Error Research ways to fix | name | Hi | 3/24
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Currently struggling with the background image to my login page | Med | Low | Doing research to solve it | name | Med | 3/24
Project Name Here