## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
I have most of the design coding done for my pages, except for one. I need to make it a little more appealing on some of the pages and add little details. I put the diamond almost in the middle of the green because I now need to connect it to my database. I am not that great when it comes to php, so I am expecting some difficulties. | 
Status as of | 27-March-19
Business Lead | Jim Worth
Project Manager | Romeo Sturkey
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/6 | 2/13
Design |  | 100% | 2/20 | 2/27
Coding |  | 80% | 3/27 | 4/1
SIT - System Test |  | 0% | 4/6 | 
UAT User Acceptance Test |  | 0% | 4/6 | 
Training and Doc |  | 0% | 4/13 | 
Deployment |  | 0% | 4/22 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Finished the Home page, contains my nav bar to navigate through the pages, also added a video
2 | Have the design of the Give page completed and linked to the cairn give URL
3 | Have my contact page designed and also have the cairn resources URL connected to it
# | Upcoming Activities (Next Period through (04/01/2019)
1 | Continue to work on the profile page
2 | Add small details to other pages, need some edit buttons, and make the visual a little more pleasing
3 | Connect the database to my pages
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | I could have trouble with PHP and getting all the information linked correctly at first. | High | High | Continue to research ways to maneuver in PHP and ask professor for some guidance | Romeo | High | 3/27-4/1
2 | I could possibly have trouble with my edit page for the profile page that I am still constructing. | Low | Med | Research some videos on how to construct the editing portion and ways to get it to function properly. | Romeo | High | 3/27-4/1
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | I tried to start using PHP, however, I was getting too caught up so I decided to step back and finish the other coding first. | High | High | Meet with professor and continue to do research to figure it out. | Romeo | High | 3/27-4/1
Cairn University Hub