## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Cleaned up cosmetic issues Slight progression with PHP | 
Status as of | 3-April-19
Business Lead | Jim Worth
Project Manager | Romeo Sturkey
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/6 | 2/13
Design |  | 100% | 2/20 | 2/27
Coding |  | 65% | 4/1 | 4/13
SIT - System Test |  | 0% | 4/6 | 4/18
UAT User Acceptance Test |  | 0% | 4/6 | 4/18
Training and Doc |  | 0% | 4/13 | 4/23 ?
Deployment |  | 0% | 4/22 | 4/28 ?
Go Live |  | 0% | 5/1 | 5/2 ?
Hyper Care |  | 0% | 5/7 | 5/7 ?
# | Key Accomplishments (Current Period)
1 | Cleaned up the contact page alongside the give page
2 | Connected profile page to database
3 | Able to use PHP to create edit boxes where user will be able to upload their own information
# | Upcoming Activities (Next Period through (04/10/2019)
1 | Get the functionality to completely work on the profile page
2 | Configure a search functionality for the home page
3 | 
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Setbacks with edit functionality(profile page) | Med | High | Once information is inputted, how does it save to the database | Romeo | High | 3/27-4/13
2 | Error with the search functionality | Med | High | Figure out the database and what information needs to be logged inside of it. | Romeo | High | 3/27-4/13
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Setbacks with Profile information being uploaded by user | Med | High | Continue to research PHP and videos on how to get it to function properly | Romeo | High | 3/27-4/13
Cairn University Hub