## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Falling behind was my worse decision because I am catching up while everyone is finalizing everything. However, I am almost there, I just have a few little things to finish. So that is why I out it almost at the yellow, but still in the red. | 
Status as of | 27-Feb-19
Business Lead | Jim Worth
Project Manager | Romeo Sturkey
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 90% | 2/27 | 
Coding |  | 10% | 4/14 | 
SIT - System Test |  | 0% | 4/21 | 
UAT User Acceptance Test |  | 0% | 4/29 | 
Training and Doc |  | 0% | 5/1 | 
Deployment |  | 0% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Finished Sitemap
2 | Finished Use Case
3 | Inputted hours
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Work on finishing Mockups
2 | Finalize everything
3 | Be officially caught up on everything and get my coding on its way
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Enter Risk 1: Need to fix Use Case | Med | Med | Add more details | name | Med | Overdue
2 | Enter Risk 2: Make Mockup better | Low | Med | Make it more exact | name | High | Overdue
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Need to have everything finalized so that I can fully commit to coding. |  |  | Enter steps to resolve | name |  | MM/DD
Project Name Here