## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Behind on coding Working towards full functionality of pages Currently behind on the functionality of search bar and some profile edits | 
Status as of | 24-April-19
Business Lead | Jim Worth
Project Manager | Romeo Sturkey
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/6 | 2/13
Design |  | 100% | 2/20 | 2/27
Coding |  | 85% | 4/1 | 4/28
SIT - System Test |  | 0% | 4/6 | 4/29
UAT User Acceptance Test |  | 0% | 4/6 | 4/29
Training and Doc |  | 0% | 4/13 | 5/2?
Deployment |  | 0% | 4/22 | 5/3
Go Live |  | 0% | 5/1 | 5/4
Hyper Care |  | 0% | 5/7 | 5/7
# | Key Accomplishments (Current Period)
1 | Fixed login page error; Fully working
2 | Fixed registration page
3 | 
# | Upcoming Activities (Next Period through (04/28/2019)
1 | Finish search bar functionality
2 | Fix errors with profile page
3 | 
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Profile page | Med | Med | Find error and fix it to become fully functional | Romeo | High | 4/28
2 | Search functionality | Med | High | Continue to work out the issues until it is working properly | Romeo | High | 4/28
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Profile page is giving some trouble when editing information | Med | High | Continue to work out the error until the information uploads correctly | Romeo | High | 4/28
Cairn University Hub